## Slide 1
Presented by
Cory Foreman
October 05, 2011
HLC FEASIBILITY STUDY Stormwater Treatment and
Runoff Reduction
Innovation • Collaboration • Inspiration
Thinking Together to Inspire
PROJECT MEETING
March 6, 2014
To change background picture, right click on the picture and select “change picture”

## Slide 2: Outline of Project Scope and Schedule
Project Coordination (continuing)
  Solicit Stormwater Quality Needs
  Obtain Development and Stormwater Improvement Plans
  Obtain Information on Stormwater Problems at HLC
  Avoid Duplication of Effort
  Solicit Input on Others to Participate
  Two Formal Presentations
Study Mapping (done)
  Use Previously Prepared Mapping
  Identify Headgates/Users, Stormwater Inflow and Outflow Locations, Existing and Future Stormwater Crossings
Water Quality Hydrology (done)
  Peak Flow Rates and Annual Volumes per Segment (of runoff water needing treatment)
  Evaluate Impacts of Upstream Detention (w or w/o WQ)

## Slide 3: Outline of Project Scope and Schedule
Canal Water Quality Hydraulic Characteristics (in process)
  Estimate Annual Volume of Water Lost to Evapotranspiration, Evaporation, and Seepage
  Estimate Volume of Storage Available for Stormwater Use
Conceptual Plan Development (in process)
  Plan for Integration into the HLC
  Type and configuration of Bioretention WQ Facilities
  Strategies to Address Aesthetic and Water Rights Issues
  Plan for Stormwater WQ Diversion Into and Out of the HLC
  Estimates of Improvement, Operation/Maintenance Costs
Conceptual Plan Evaluation
  Quantify Benefits
  Identify Constraints and Solutions for Implementation
  Evaluate Economic Feasibility

## Slide 4: Outline of Project Scope and Schedule
Pilot Project Preliminary Design
  Downstream of Fairmont Cemetery
Project Schedule
  300 days (10 months)
    Month 1 - Study Mapping
    Months 2, 3, and 4 – Water Quality Hydrology and Canal Water Quality Hydraulic Characteristics
    Months 5, 6, and 7 – Conceptual Plan Development
    Months 8, 9, and 10 – Conceptual Plan Evaluation and Pilot Project Preliminary Design
Deliverables
  Written Report
  Feasibility Drawings Compatible with ArcView
  Technical Appendix

## Slide 5: Design Reach Comments
Douglas County
  Reach 2 – Little Willow Creek enters directly into the canal at the upstream end of the reach

## Slide 6: Design Reach Comments
Douglas County
  Stormwater discharges to Mclellen Reservoir – Discouraged in the past
  Owned/operated by City of Englewood

## Slide 7: Design Reach Comments
City of Littleton
  Stream stabilization project on Jackass Gulch (2014)
  Reach 16 - Discharge to roadside ditch, extend to existing storm sewer?

## Slide 8: Design Reach Comments
City of Littleton
  Discharge to Horseshoe Park, adjacent neighborhood has a strong interest in this natural open space. Public outreach is strongly encouraged during the design process.

## Slide 9: Design Reach Comments
SEMSWA
  Discharge point at Orchard Road, storm sewer shown does not exist. (SEMSWA GIS data shows a 24” RCP)
  Orchard Road gutter flow could be diverted into canal

## Slide 10: Design Reach Comments
SEMSWA
  Reach 18 – 60” RCP inflow location

## Slide 11: Design Reach Comments
SEMSWA/UDFCD
  Add an inflow location at Iliff Ave.
  Iliff Ave Corridor Study, canal could provide WQCV for tributary areas east of canal

## Slide 12: Design Reach Comments
Greenwood Village
  Reach 23 exists in a “horseshoe”, naturally drains to canal
  Reach discharges to a CDOT system (University Blvd)
  Ridge down the center of the basin, flows north and south

## Slide 13: Design Reach Comments
Greenwood Village
  Reach 25 – Inflow/discharge locations at existing EDBs
  Reach 26 - Greenwood Gulch flows into the canal and discharges further downstream

## Slide 14: Pilot Reach Selection
Pilot Reach Selection
  Selection Criteria
    Downstream of current canal users (Fairmount Cemetery?)
    Reach that spans multiple jurisdictions
    Detailed mapping already available
      1-ft contour mapping preferable
    Storm sewer survey or as-built drawings available for entire reach at the inflow / outflow locations
    Locations available for new forebays with maintenance accessibility
    Minimal existing water quality facilities in the tributary watershed
    Diversions into and out of canal hydraulically feasible without large extensions of storm sewers

## Slide 15: Pilot Reach Selection
Pilot Reach Selection
  Pilot reach would include Denver and Aurora

## Slide 16: Water Rights / Water Quality
Water Rights
Excerpts from Sate Engineer’s “Policy” as of May 21, 2011
Administrative Approach for Storm Water Management
The detention areas must release all of the water detained from the site within 72 hours of the end of a precipitation event. Such detention should be designed to release the water from the site as quickly as downstream conditions allow and should minimize consumption from vegetation.
An infiltration area must be designed to infiltrate the water as quickly as possible and shall not result in an exposed water surface beyond 72 hours after the end of a precipitation event. An infiltration area must be designed to minimize consumption from vegetation.
Focus is on whether there is a significant identifiable increase in evapotranspiration from vegetation over the current conditions due to the construction of the water quality facilities
Coordinating with Denver Water on this evaluation
Adjusting design reaches to observe natural watershed boundaries

## Slide 17: Water Rights / Water Quality
Water Quality
  Using WQ-COSM to determine historical number, frequency, and size of storm events
  Use storm event data to compute estimated percent removal of storm water pollutants based upon the volume stored and released over 72 hours.
  Use historic data on infiltration to estimate approximate amount of additional pollutant removal in portion of runoff estimated to infiltrate.
  Prepare a summary of the expected performance of the individual canal reaches and a cumulative summary of the potential pollutant removal from the entire High Line Canal system.

## Slide 18: Benefits / Costs Analysis
Benefits / Costs Analysis
  Costs
    Construction costs
      In-canal facilities (structures / construction and maintenance access)
      Diversion and return facilities (structures, pipes, and energy dissipation)
      Forebay or equivalent sediment removal facilities / structures
      Upstream storm sewer extensions for hydraulic feasibility
      Return flow pipelines to appropriate return flow locations
      Easements / right-of-way and permitting
    Operation and maintenance costs
      Facilities upkeep / repair / replacement
      Debris and sediment removal and disposal

## Slide 19: Benefits / Costs Analysis
Benefits / Costs Analysis
  Benefits
    Quantified monetary benefits
      Tree watering costs provided in the HLC Preservation and Enhancement Planning Study (HLC Working Group). Estimate the extent that these costs may be reduced by the proposed improvements
      Reduced need and costs for construction of local water quality facilities as may be needed to meet stormwater permit requirements
    Qualified monetary benefits
      Estimated removal percentages and amounts of various pollutants
      Estimated value of retained recreational use and retained trees
      Other benefits?

## Slide 20: Coming Up…
Water Rights / Water Quality
  Water rights review
  Quantification of water quality benefits
Cost Estimates of Facilities
Discussion of Conceptual Design Issues
Draft Report